## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  | 1 |  |  | Plan Duration
ACTIVITY ID | Activity description | PLAN START | PLAN DURATION | PERIODS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Project Kickoff | Initiate project, define goals, roles, and timelines. | 1 | 1
Requirement Gathering | Gather detailed project needs and expectations. | 2 | 3
Design Phase | Create website layout and user interface mockups. | 5 | 4
Content Creation | Develop text, images, and multimedia for the site. | 9 | 6
Development Phase | Build and code the functional website. | 15 | 8
SEO Implementation | Optimize site content for search engines. | 23 | 2
Testing Phase | Test functionality, usability, and performance. | 25 | 3
Bug Resolution | Fix identified issues and ensure site stability. | 28 | 2
Marketing Preparation | Plan promotional strategies for the launch. | 30 | 3
Website Launch | Make the site live for public access. | 33 | 1
Post-launch Support | Maintain, update, and improve site after launch. | 33 | 2